## Module Progress
S.No | Module | Major Completed Features | Overall Completion | Pending Work | Department
1 | SCM Queue | SCM Queue, OVF Preview, Hold/Unhold OVF, Freight & Finance Updates, Create Vendor PO, Finalize PO, Company PO Numbering, CRM Handoff, Queue Filters | 95% | Final testing, bug fixes, performance optimization, edge case handling, documentation | Procurement
2 | Purchase Orders | Create PO, Edit PO, Finalize PO, PO PDF, PO Excel Export, Draft/Issued Status, PO Details | 100% | Completed | Procurement
3 | Goods Receipt Note | Partial Receipt, Receipt Batches, GRN PDF, Receipt History, Serial Number Management | 100% | Completed | Procurement
4 | Vendors | Vendor Master, Vendor List, Add/Edit Vendor, Vendor Details | 95% | Vendor validation improvements, testing | Procurement
5 | Vendor Invoices | Upload Invoice, Invoice Extraction, Vendor Invoice Storage, Receipt Batch Integration, Invoice History | 86% | Invoice approval workflow, GST validation,Azure credential for mail transfer | Procurement
6 | PO Number Generation | Auto Company PO Number, Entity-wise Numbering, Preview Next PO Number | 100% | Completed | Procurement
7 | Purchase Order PDF | Company PO PDF, Printable Format, Download Support | 100% | Completed | Procurement
8 | Purchase Order Export | Excel Export, Filtered Export, Download Report | 100% | Completed | Procurement
9 | Freight & Finance Management | Freight Charges, Additional Charges, Finance %, Commercial Updates | 95% | Validation, calculation optimization | Procurement
10 | Procurement Dashboard | SCM Queue Overview, Recent Activities, Status Counters, Dashboard Widgets | 88% | Additional dashboard widgets, charts, KPI improvement | Procurement
11 | Reports & Analytics | Procurement Reports, PO Reports, Invoice Reports, Export Support | 85% | Advanced reports, dashboard filters, scheduled exports, analytics enhancements | Procurement
12 | Procurement Inventory | Inventory Listing, Inventory Import, Create PO from Inventory, Inventory Reports | 82% | Inventory reconciliation, stock valuation, validations, reporting graphs | Inventory
13 | Stock Summary | Inventory Summary, Available Stock, Received Quantity, Billing Quantity | 90% | Additional summary metrics, filters | Inventory
14 | Stock Movement | Stock In, Stock Out, Transfer Between Warehouses, Movement History | 88% | Approval workflow, movement audit logs | Inventory
15 | Inventory Adjustments | Stock Adjustments, Damaged Stock, Quantity Corrections | 85% | Approval process, reason tracking, audit logs | Inventory
16 | Delivery Challan | Create Challan, Edit Challan, View Challan, Challan PDF, PO Linking | 100% | Completed | Inventory
17 | Delivery Status | Delivery Status Tracking, Dispatch Status, Delivery Timeline, PO Reference | 93% | Delivery notifications, status automation, tracking enhancements | Inventory
18 | Receipt Batch Management | Batch Creation, Batch History, GRN Number Generation, Receipt Tracking | 100% | Completed | Inventory