## Cover
Enterprise ERP — Feature Catalog
As of 2026-08-14 · Focus: work delivered to date (Asset Management + platform foundations)
How to read this workbook
Topic | Description
Sheet: Features | One row per delivered capability. Filter by Module, Area, or Status.
Sheet: Change Requests | CR-001 through CR-006 — the Asset change-request track after FP-ASSET-019.
Sheet: Feature Packages | Original Asset feature packages (FP-ASSET-002 … 019) still in the product.
Sheet: Platform modules | Wider ERP modules that exist in the product catalog (not all were the recent Asset demo focus).
Status = Done | Shipped in UI and/or API for the current walkthrough.
Status = Partial | Built but gated (e.g. Excel cutover still NO-GO until a frozen workbook is measured).
Demo vs live API | Register, Issue wizard, and Operations dashboard keep working with demo data when Docker/Postgres is down.
Key walkthrough paths
Item | Path
Frontend | http://localhost:3000
Backend API | http://localhost:8000
API docs | http://localhost:8000/docs
Asset hub | /assets
Operations dashboard | /assets/operations
Asset Register | /assets/assets
Add Asset | /assets/assets/new
Issue Asset | /assets/asset-assignments/new
Return Asset | /assets/asset-assignments/return
Excel import | /assets/inventory-import

## Features
# | Module | Area | Feature | What we delivered | Status | Source | Route / API
1 | Platform | Auth | Login & session | Form-based login with token storage and hard redirect after sign-in so the app lands on the correct module (e.g. Assets). | Done | Runtime | /login
2 | Platform | Foundation | Tenants, users, RBAC | Tenant isolation, user accounts, roles, and permission catalog backing every business module. | Done | Foundation | /foundation
3 | Platform | Foundation | Workflow engine | Reusable workflow definitions and running instances used by assignment, transfer, maintenance, disposal, and related documents. | Done | Foundation | /workflows
4 | Platform | Foundation | Notifications & audit | Notification rules plus audit logs for create/update/status transitions (including operational-status and discovery apply). | Done | Foundation | /audit
5 | Platform | Organization | Company / branch / department / location | Organization masters used by Asset Register, assignment, and dashboard branch filter. | Done | Organization | /organization
6 | Platform | Master Data | Employees, vendors, products | Employee master drives Issue Asset; vendors/products support portal and registration lookups. | Done | Master Data | /master-data
7 | Asset Management | Register | Asset Register (inventory table) | Single operational register with search, filters, pagination, expandable rows, and Excel-parity columns (tag, name, manufacturer, model, configuration, holder, employee ID, department, branch, statuses, issue date, location). | Done | CR-004 Phase 3.4 | /assets/assets
8 | Asset Management | Register | Add Asset wizard | Multi-step registration with category, branch, and review. Successful create returns to the register with toast, soft refresh, and row highlight. Demo path still lands on the register when API IDs are not live. | Done | CR-006 Task 1 | /assets/assets/new
9 | Asset Management | Register | Branch on Add Asset | Branch is required, remapped when API branches replace demo IDs, shown on Review, and persisted so the new row appears on Asset Register. | Done | Demo / Register | /assets/assets/new
10 | Asset Management | Register | Operational status dropdown (IT Admin) | Register Operational Status is an editable dropdown (not a static badge). Changing status updates the row immediately, stores a demo override, and best-effort PATCHes the API. Assigned assets stay out of Issue Asset. | Done | Ops UI | /assets/assets
11 | Asset Management | Register | Status-driven actions | Allocate / Return / Edit / Delete / Dispose visibility follows operational status. Invalid actions are hidden in the ⋮ menu and drawer; navigation is blocked client-side with backend validation as the second layer. | Done | CR-006 Task 5 | Register + drawer
12 | Asset Management | Register | Asset detail drawer workspace | Row click opens an in-place drawer (no page leave): Overview, Configuration, Assignment, History, Timeline, Documents. Header QR plus sticky action bar (Allocate / Return / etc.). | Done | CR-005 Phase 2 | Inventory drawer
13 | Asset Management | Register | Current holder & Excel parity fields | Holder is derived from active assignment when Assigned. Expandable/drawer show Earlier Used By, delivery challan, delivery status, remarks, phone — matching the Excel register columns. | Done | CR-004 Phase 6 | Register + drawer
14 | Asset Management | Register | Demo register data fill | Seed demo assets (laptops + projector) plus sessionStorage registrations so every column and drawer section has complete data instead of dashes. | Done | Demo data | sessionStorage + seeds
15 | Asset Management | Assignment | Issue Asset wizard (5 steps) | Employee Information → Asset Information → Issued Items → Assignment Details → Review & Confirm. Draft save, submit, and activate against the assignment API. | Done | CR-004 Phase 5B | /assets/asset-assignments/new
16 | Asset Management | Assignment | Ready-To-Move picklist only | Asset Information lists only Ready To Move stock. Already Assigned assets never appear. Guest/demo load uses demo ready assets and fills Branch from the selected asset. | Done | Ops UI + CR-004 | Issue wizard step 2
17 | Asset Management | Assignment | Employee step (master data) | Searchable employee pick with auto-fill of code, department, designation, branch, and employment status from Master Data (plus demo employee when not signed in). | Done | CR-004 Employee Step | Issue wizard step 1
18 | Asset Management | Assignment | Delivery reference & remarks | Delivery challan number/status and assignment remarks captured on issue; return remarks and return condition on return. Stored on assignment documents (migration 0487). | Done | CR-004 Phase 5A | Assignment API
19 | Asset Management | Assignment | Return Asset wizard (4 steps) | Summary → Condition → Remarks → Review. Completes return, restores Ready To Move, and clears holder on the register. | Done | CR-004 Phase 5B | /assets/asset-assignments/return
20 | Asset Management | Assignment | Assignment list CRUD workspace | List of assignments with Create (wizard), Edit draft, Return, and Delete/cancel draft. Rules keep drafts vs active documents distinct. | Done | CR-004 CRUD | /assets/asset-assignments
21 | Asset Management | Assignment | Drawer → Allocate with prefilled asset | Allocate from register/drawer opens Issue wizard with that asset locked, skips duplicate selection, and returns through the existing refresh path. | Done | CR-006 Task 2 | Drawer CTA
22 | Asset Management | Assignment | Post-assign register sync | After successful allocation: soft refresh, success toast, highlighted row, drawer/history/timeline/action bar show Assigned + holder without a full page reload. | Done | CR-006 Task 3 | Register
23 | Asset Management | Assignment | Post-return register sync | After successful return: soft refresh, toast, highlight, holder/employee/issue date cleared when Ready, actions restore Allocate. | Done | CR-006 Task 4 | Register
24 | Asset Management | Assignment | Deep links & draft resume | Query params assetId, employeeId, draftId, assignmentId, intent=return map to wizard containers so inventory and emails can resume work. | Done | CR-004 Task 5 | Wizard hosts
25 | Asset Management | Dashboard | Module hub | Landing at /assets with three primary modules: Asset Register, Asset Allocation, Add Asset — each routing to existing workflows. | Done | CR-005 hub | /assets
26 | Asset Management | Dashboard | Asset Operations workspace | Full operations page: sticky toolbar, quick actions, KPI strip, health + pending, Ready/Disposal queues, embedded register, recent activity. | Done | CR-005 Phases 1–4 | /assets/operations
27 | Asset Management | Dashboard | KPI strip | Live (or demo fallback) counts: Total Assets, Ready To Move, Assigned, Pending Disposal, Retired, Disposed from dashboard-summary API. | Done | CR-004 / CR-005 | KPI cards
28 | Asset Management | Dashboard | Quick actions | Add Asset, Allocate, Return, Import, Export cards plus matching sticky toolbar buttons. | Done | CR-005 Phase 3–4 | Operations workspace
29 | Asset Management | Dashboard | Ready To Move & Disposal queues | Queue cards list ready stock for allocation and pending-disposal assets; empty copy tells IT Admin to mark Ready To Move from the register dropdown. | Done | CR-005 + demo queues | Operations workspace
30 | Asset Management | Dashboard | Health summary & pending actions | Compact health widget from KPI mix; pending actions (allocate ready, return assigned, disposal, maintenance) with navigation. | Done | CR-005 Phase 4 | Operations workspace
31 | Asset Management | Dashboard | Recent activity | Last 10 events (registered / assigned / transferred / disposed) grouped Today / Yesterday / Earlier. | Done | CR-005 Phase 3–4 | Operations workspace
32 | Asset Management | Dashboard | Unified branch + global search | One branch selector drives KPIs, queues, register, and activity. Global search applies to the embedded register without a second search box. | Done | CR-005 Phase 3–4 | Sticky toolbar
33 | Asset Management | Dashboard | Demo dashboard when API unauthenticated | If summary APIs fail or require auth, workspace still shows demo KPIs, queues, and activity so walkthroughs are usable. | Done | Demo fallback | Operations container
34 | Asset Management | Navigation | Full Assets sidebar | Restored full catalog (was trimmed to 3 MVP links): Dashboard, Asset Operations, Register, Add Asset, Configuration, Operations (Allocation/Transfers/Maintenance), Lifecycle, Compliance, Extended, QR, Reports, Settings. | Done | Nav restore | Assets sidebar
35 | Asset Management | Navigation | Workspace secondary tabs | Horizontal workspace tabs match the full sidebar catalog. | Done | Nav restore | Assets workspace nav
36 | Asset Management | Status engine | Operational status (domain) | Separate operational_status column and enum (Ready To Move, Assigned, Pending Disposal, Retired, Disposed, etc.) distinct from lifecycle status. | Done | CR-004 Phase 2A | ast_asset
37 | Asset Management | Status engine | Transition engine | AssetOperationalStatusEngine is the sole transition authority. Workflows (register / assign / return / dispose) call the service — no free-form PATCH of status on the API (UI dropdown is a demo/IT-admin overlay with best-effort update). | Done | CR-004 Phase 2B | Status service
38 | Asset Management | Status engine | Dashboard summary API | GET /assets/dashboard-summary returns ops bucket counts; register list filters by operational_status. | Done | CR-004 Phase 2C | GET dashboard-summary
39 | Asset Management | Configuration | Asset categories | Create, edit, deactivate, reactivate (soft delete only). Cannot deactivate while operational assets reference the category. Registration dropdown shows active categories only. | Done | CR-001 | /assets/asset-categories
40 | Asset Management | Configuration | Asset types / locations / departments | Type catalog plus organization locations and departments used on register and assignment. | Done | FP + org masters | /assets/asset-types
41 | Asset Management | Portal | Asset Information Portal | Read-only portal from View: overview, assignment, warranty, insurance. QR generated in the browser (never stored as an image). | Done | CR-002 | /assets/information-portal/{id}
42 | Asset Management | Portal | QR self-service (authenticated) | QR encodes self-service URL; authenticated page shows a redacted asset DTO. No public unauthenticated access. | Done | CR-002 | /assets/self-service/{id}
43 | Asset Management | Discovery | Hardware discovery | Generate Windows/Linux/macOS command, paste output, parse preview, then apply allowlisted identity fields. No auto-persist on parse. Audit event discovery_apply. | Done | CR-003 | Portal discovery section
44 | Asset Management | Operations | Transfers | Asset transfer documents with workflow (draft → submit → approve → complete) and UI list/detail. | Done | FP-ASSET-002 | /assets/asset-transfers
45 | Asset Management | Operations | Maintenance work orders | Maintenance documents with workflow, linked to assets and plans. | Done | FP-ASSET-004 | /assets/asset-maintenances
46 | Asset Management | Lifecycle | Disposal / retirement | Disposal documents, governance permissions, open-status index, document sequence. Asset status updates on post only. | Done | FP-ASSET-005 | /assets/asset-disposals
47 | Asset Management | Lifecycle | Depreciation | Depreciation runs and postings against asset book value. | Done | FP-ASSET-006 | /assets/asset-depreciations
48 | Asset Management | Lifecycle | Revaluation | Revaluation documents with workflow and book-value impact. | Done | FP-ASSET-007 | /assets/asset-revaluations
49 | Asset Management | Compliance | Physical audits | Physical verification / audit documents and UI. | Done | FP-ASSET-008 | /assets/asset-audits
50 | Asset Management | Compliance | Warranties | Warranty coverage records on assets. | Done | FP-ASSET-009 | /assets/asset-warranties
51 | Asset Management | Compliance | Insurance | Insurance policies linked to assets. | Done | FP-ASSET-010 | /assets/asset-insurances
52 | Asset Management | Extended | Maintenance plans | Preventive maintenance schedules feeding work orders. | Done | FP-ASSET-011 | /assets/maintenance-plans
53 | Asset Management | Extended | Asset locations | Asset-specific location assignments; integrates with transfers. | Done | FP-ASSET-012 | /assets/asset-locations
54 | Asset Management | Extended | Service history | Completed service events; maintenance integration. | Done | FP-ASSET-013 | /assets/service-histories
55 | Asset Management | Extended | Checklists | Inspection and audit checklists with lifecycle fidelity. | Done | FP-ASSET-014 | /assets/asset-checklists
56 | Asset Management | Extended | Meter readings | Usage / meter capture against assets. | Done | FP-ASSET-015 | /assets/meter-readings
57 | Asset Management | Extended | Documents | Asset document attachments with lifecycle fidelity. | Done | FP-ASSET-016 | /assets/asset-documents
58 | Asset Management | Extended | Asset notifications | Asset-specific notification rules on the platform notification engine. | Done | FP-ASSET-017 | /assets/asset-notifications
59 | Asset Management | Reporting | Asset reports | Inventory, assignment, and maintenance report APIs and UI. | Done | FP-ASSET-018 | /assets/reports
60 | Asset Management | Extended | Components | Asset component breakdown (parent/child hardware). | Done | FP-ASSET-019 | /assets/asset-components
61 | Asset Management | Labels | QR / Barcode workspace | Generate and scan asset labels from the module nav. | Done | CR-002 + FP | /assets/qr-barcode
62 | Asset Management | Excel | Register Excel / CSV export | Toolbar export of the current Asset Register to Excel/CSV with locked column names. | Done | CR-004 Phase 7A | Register Export
63 | Asset Management | Excel | Excel import preview | Upload customer Excel, validate, and preview rows with no writes until commit. | Done | CR-004 Phase 8A | /assets/inventory-import
64 | Asset Management | Excel | Excel import commit engine | POST /assets/assets/import batches validated rows, handles duplicates, and applies operational-status paths. | Done | CR-004 Phase 8B | Import API
65 | Asset Management | Excel | Migration reconciliation kit | Excel↔ERP difference register, validation report, and go-live checklist. Org-wide Excel stop remains NO-GO until a frozen workbook is measured. | Partial | CR-004 Phase 8C | Docs + import UI

## Change Requests
CR | Title | Status | Date | What we delivered
CR-001 | Asset Category Management Enhancement | Completed | 2026-07-30 | Category CRUD, deactivate/reactivate with referential guard, dedicated workspace, active-only dropdown on registration.
CR-002 | Asset Information Portal + QR Self-Service | Completed | 2026-07-31 | Read-only portal, dynamic client-side QR, authenticated self-service DTO. No public access, no stored QR images.
CR-003 | Asset Discovery Module | Completed | 2026-07-31 | OS command generator, parse preview, apply allowlisted hardware fields, JSONB discovery_profile, audit discovery_apply.
CR-004 | IT Asset Operations & Inventory Management | Substantially complete (through 8C) | 2026-08-03 to 2026-08-06 | Operational status engine, operations dashboard, inventory register, Issue/Return wizards, Excel import/export, navigation E2E. Sidebar polish originally deferred then restored in product UI.
CR-005 | Asset Operations Workspace | Completed (Phases 1–4) | 2026-08-06 | KPI + embedded register, tabbed detail drawer, quick actions + activity, sticky toolbar / health / pending / queues. Entry: /assets/operations.
CR-006 | Asset Lifecycle Integration | Completed (Tasks 1–5) | 2026-08-06 | Registration lands on register; drawer Allocate prefill; assign/return soft-sync; status-driven menus and CTAs.

## Feature Packages
Package | Feature | What we delivered | Status | Typical route
FP-ASSET-002 | Transfers | Transfer documents with workflow and UI list/detail. | Done | /assets/asset-transfers
FP-ASSET-003 | Assignment (allocation) | Custodian assignment documents; later extended by CR-004 wizards and CR-006 sync. | Done | /assets/asset-assignments
FP-ASSET-004 | Maintenance work orders | Maintenance documents with workflow linked to assets and plans. | Done | /assets/asset-maintenances
FP-ASSET-005 | Disposal / retirement | Disposal governance, permissions, sequences; status update on post. | Done | /assets/asset-disposals
FP-ASSET-006 | Depreciation | Depreciation runs and postings. | Done | /assets/asset-depreciations
FP-ASSET-007 | Revaluation | Revaluation documents and book-value impact. | Done | /assets/asset-revaluations
FP-ASSET-008 | Audits | Physical verification / audit documents. | Done | /assets/asset-audits
FP-ASSET-009 | Warranties | Warranty coverage records. | Done | /assets/asset-warranties
FP-ASSET-010 | Insurance | Insurance policies for assets. | Done | /assets/asset-insurances
FP-ASSET-011 | Maintenance plans | Preventive schedules feeding work orders. | Done | /assets/maintenance-plans
FP-ASSET-012 | Asset locations | Asset-specific location assignments. | Done | /assets/asset-locations
FP-ASSET-013 | Service history | Completed service events. | Done | /assets/service-histories
FP-ASSET-014 | Checklists | Inspection and audit checklists. | Done | /assets/asset-checklists
FP-ASSET-015 | Meter readings | Usage and meter capture. | Done | /assets/meter-readings
FP-ASSET-016 | Documents | Asset document attachments. | Done | /assets/asset-documents
FP-ASSET-017 | Notifications | Asset notification rules. | Done | /assets/asset-notifications
FP-ASSET-018 | Reports | Inventory, assignment, and maintenance reports. | Done | /assets/reports
FP-ASSET-019 | Components | Asset component breakdown. | Done | /assets/asset-components

## Platform modules
Module group | Feature | Description
Foundation | Tenants | Multi-tenant registry with isolation keys on transactional tables.
Foundation | Users & sessions | User accounts and login sessions.
Foundation | Roles & permissions | RBAC roles and permission catalog.
Foundation | Workflows | Definition + instance engine used by business documents.
Foundation | Notifications | Notification engine and templates.
Foundation | Audit | Cross-module audit log.
Foundation | Settings | System settings.
Organization | Companies | Legal entities.
Organization | Branches | Operating branches (Asset dashboard filter).
Organization | Departments | Departments for assignment and register.
Organization | Business units | Business unit hierarchy.
Organization | Locations | Physical locations.
Organization | Cost / profit centers | Finance org dimensions.
Master Data | Employees | Employee master (Issue Asset step 1).
Master Data | Customers | Customer master.
Master Data | Vendors | Vendor master.
Master Data | Products & categories | Product catalog.
Master Data | UOM / currencies / taxes | Shared catalogs.
Master Data | Warehouses | Warehouse master.
Finance | Chart of accounts / journals / GL / AR / AP | Core financial ledgers (platform module).
Procurement | Purchase documents | Procurement operations module.
Inventory | Stock operations | Inventory operations module.
Sales | Sales documents | Sales operations module.
Manufacturing | Production | Manufacturing operations module.
Quality | Quality | Quality operations module.
CRM | CRM | CRM operations module.
HR / Payroll / Recruitment | People ops | HR, payroll, and recruitment modules.
Projects | Projects | Project / site installation module.
Service / Helpdesk | After-sales | Service and helpdesk modules.
Documents / GRC / Analytics / Integration / eCommerce / Portal | Supporting modules | Additional ERP modules registered in the frontend module catalog.

## Summary counts
By area (Features sheet)
Area | Feature count
Assignment | 10
Auth | 1
Compliance | 3
Configuration | 2
Dashboard | 9
Discovery | 1
Excel | 4
Extended | 8
Foundation | 3
Labels | 1
Lifecycle | 3
Master Data | 1
Navigation | 2
Operations | 2
Organization | 1
Portal | 2
Register | 8
Reporting | 1
Status engine | 3
By status
Status | Feature count
Done | 64
Partial | 1
Total features listed | 65